## Template
<PRACTICE NAME>
| CONTINUITY OF CARE PLAN |  |  | 2021-02-01 |  |  |  | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | To auto add more dates right click and drag the last month along
|  | Owner | Status | 1 | 2 | 3 | 4
Tasks
Milestones |  |  | Complete
On track
Delayed
Overdue
| Key Activities | Owner | Status
| Download copy of plan |  | Complete
M | Identify key milestones |  | On track

## Practice Example
Continuity of Care Project Plan
Newtown Practice |  |  | 2019-08-01 |  |  |  | 2019-09-01 |  |  |  | 2019-10-01 |  |  |  |  | 2019-11-01 |  |  | 2019-12-01 |  |  |  |  | 2020-01-01 |  |  |  | 2020-02-01 |  |  |  | 2020-03-01
|  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Complete
On track
Delayed
Overdue
Key Activities | Owner | Status
Working with patients
Patient Survey | Practice/MMcD | Complete | bar: 2019-08-01 1
Practice Staff Survey - online | Practice/MMcD | Complete | bar: 2019-08-01 1 to 2019-08-01 4
Patient Interviews on Leaflet | OCL | Complete | bar: 2019-08-01 4
Identifying & assigning patients
EMIS Usual GP tool to extract data | HK | Complete | bar: 2019-10-01 1
Select c.30 FA cohort - divide into MH & Physical | Practice | Complete | bar: 2019-11-01 2 to 2019-11-01 3
Usual GP reviews their FA cohort patients to confirm suitable | GPs | Complete | bar: 2019-11-01 4 to 2019-12-01 1
Assign GP & Buddy based on Tool & clinical confirmation | PM | Complete | bar: 2019-12-01 2
Check FA cohort allocated evenly across teams | PM | Complete | bar: 2019-12-01 2
Changes to process
Check Usual GP field for FA cohort updated | CD | Complete | bar: 2020-01-01 2
Check Usual GP correct for scripts | CD | Complete | bar: 2020-01-01 2
Letters to FA cohort with no of appts + GP & Buddy | CD | Complete | bar: 2020-01-01 2
Confirm wording for pop up protocol reminder if using | MN | Complete | bar: 2020-01-01 2
Pop up protocol - guidance from Colette Buckley | MN | Complete | bar: 2020-01-01 2
Pop protocol wording and set up | MN | Complete | bar: 2020-01-01 3
Confirm formal start date to project | HK | Complete
Capture any Lessons Learnt or RAID | PM | On track | bar: 2020-01-01 1 to 2020-03-01 4
Measures of success - what are they for this cohort tbc | OCL/Practice | Complete | bar: 2019-12-01 2
Measure success and agree next steps (roll out/amend) | OCL/Practice | On track | bar: 2020-03-01 2 to 2020-03-01 3
Communication staff and patients
Staff Comms & Training - planning | OCL/Practice | Complete | bar: 2020-01-01 2
Staff Comms & Training - deliver | PM | Complete | bar: 2020-01-01 2
PPG - presentation | PM | Complete
Patient Info Campaign begins - Poster, Leaflet, Animation | CD | Complete | bar: 2020-01-01 4
Practice Social Media begins - Website, Tweets | CD | Complete | bar: 2020-01-01 4
Taking time to complete a plan with the key tasks:
- helps the practice to think through what is needed, when and who can do it
- enables the practice team to see what's planned and to track progress.
In this example, the practice grouped activities but you may prefer to list the key tasks in the order they need to be done.